## Blad1
Kanyerus projekt 1 year | Budget and expenditures
All figures in SEK
Activities/expenditure | SEK in the budget | SEK used in the project
Intro meeting for community leader | 7200 | 7170
Training för groups | 12500 | 12520
Groups having regular meeting | no budget
Organising community days, youth meet | 18200 | 21500 | Some more activites were done compared to planned
Organisera “village walks” för att propagera för projekt teman. | 6200 | 7600 | Some more activites were done compared to planned
Skolbesök, kyrkobesök, besök till andra tillställningar och bysamlingar. | not budget
T shirts | 4000 | 4000
PPEs - flyttat till youth meeting |  |  | This post was moved to nb 8, for extra youth meeting
Identifications | 200 |  | Not used
Group register | 100 |  | Not used
Fuel | 6000 | 2350 | Selina that has worked with the project has mainly gone to the village with the jeepline
Other transport costs | 7000 | 9200 | This includes some vehicle costs and costs for the group to travel to some activities
Admin | 3000 | 1700
Project filed officer in village | 6800 | 8800 | Salary for the project field officer has taken the full responsibility for the project,
CHEW | 3600 | 0 | The Community Health Extension Worker has been involved but not paid by the project, used for the field officer
Project management, follow-up and controll | 3000 | 3000 | Project management, follow-up by Daniel and Jacinta
| 77800 | 77840